## Time Tracking Report
Waterfront Games
Issue Type | Key | Status | Priority | Summary | Original Time Estimated (min) | Σ | Estimated Time Remaining (min) | Σ | Total Time Spent (min) | Σ | Accuracy | Σ | Accuracy (%) | Σ
Story | MGPG9B-2 | Done | Major | Program the Player Dash control | 60 | 60 | 0 | 0 | 120 | 120 | -60 | -60 | -100 | -100
Story | MGPG9B-3 | Done | Major | Program the Ball physics for our game | 180 | 180 | 0 | 0 | 180 | 180 | 0 | 0 | 0 | 0
Story | MGPG9B-4 | Done | Major | Design a new art style with accompanying moodboard | 60 | 60 | 0 | 0 | 150 | 150 | -90 | -90 | -150 | -150
Story | MGPG9B-5 | Done | Major | Design assets for the Player and the Ball | 120 | 120 | 0 | 0 | 120 | 120 | 0 | 0 | 0 | 0
Story | MGPG9B-6 | Done | Major | Design assets for the Player and the Ball | 120 | 120 | 0 | 0 | 120 | 120 | 0 | 0 | 0 | 0
Story | MGPG9B-7 | Done | Major | Design assets for the Arena | 120 | 120 | 0 | 0 | 120 | 120 | 0 | 0 | 0 | 0
Story | MGPG9B-8 | Done | Major | Design assets for the Arena | 120 | 120 | 0 | 0 | 120 | 120 | 0 | 0 | 0 | 0
Story | MGPG9B-9 | Done | Major | Design assets for the User Interface | 120 | 120 | 0 | 0 | 120 | 120 | 0 | 0 | 0 | 0
Story | MGPG9B-10 | Done | Major | Design assets for the User Interface | 120 | 120 | 0 | 0 | 120 | 120 | 0 | 0 | 0 | 0
Story | MGPG9B-14 | Done | Major | Program the catch mechanic | 120 | 120 | 0 | 0 | 120 | 120 | 0 | 0 | 0 | 0
Story | MGPG9B-15 | Done | Major | Program the throw mechanic | 60 | 60 | 0 | 0 | 60 | 60 | 0 | 0 | 0 | 0
Story | MGPG9B-16 | Done | Major | Finish programming the ball physics | 180 | 180 | 0 | 0 | 240 | 240 | -60 | -60 | -33 | -33
Story | MGPG9B-19 | Done | Major | Design the player concepts that we discussed in the meeting | 180 | 180 | 0 | 0 | 180 | 180 | 0 | 0 | 0 | 0
Story | MGPG9B-21 | Done | Major | Design the arena floor for our game using the art style we have agreed upon | 180 | 180 | 0 | 0 | 180 | 180 | 0 | 0 | 0 | 0
Story | MGPG9B-22 | Done | Major | Continue to design more assets that will be put into the game | 180 | 180 | 0 | 0 | 180 | 180 | 0 | 0 | 0 | 0
Story | MGPG9B-23 | Done | Major | Implement the scoring system into the game | 120 | 120 | 0 | 0 | 120 | 120 | 0 | 0 | 0 | 0
Story | MGPG9B-24 | Done | Major | Code the power system into the throw mechanic | 180 | 180 | 0 | 0 | 180 | 180 | 0 | 0 | 0 | 0
Story | MGPG9B-25 | Done | Major | Create the halfway point that neither player can cross | 60 | 60 | 0 | 0 | 60 | 60 | 0 | 0 | 0 | 0
Story | MGPG9B-26 | Done | Major | Draw the asset for the goal | 60 | 60 | 0 | 0 | 90 | 90 | -30 | -30 | -50 | -50
Story | MGPG9B-27 | Done | Major | Create a sprite sheet for animation in the ground breaking | 120 | 120 | 0 | 0 | 120 | 120 | 0 | 0 | 0 | 0
Story | MGPG9B-28 | Done | Major | Re-create the floor to the correct resolution | 90 | 90 | 0 | 0 | 90 | 90 | 0 | 0 | 0 | 0
Story | MGPG9B-29 | Done | Major | Research UI techniques | 90 | 90 | 0 | 0 | 90 | 90 | 0 | 0 | 0 | 0
Story | MGPG9B-30 | Done | Major | Draw some of the character concepts that you have designed | 180 | 180 | 0 | 0 | 180 | 180 | 0 | 0 | 0 | 0
Story | MGPG9B-33 | Done | Major | Create a presentation using the template from our first | 120 | 120 | 0 | 0 | 120 | 120 | 0 | 0 | 0 | 0
Story | MGPG9B-34 | Done | Major | Turn the character concepts into finalised artwork | 120 | 120 | 0 | 0 | 120 | 120 | 0 | 0 | 0 | 0
Story | MGPG9B-35 | Done | Major | Create UI elements | 120 | 120 | 0 | 0 | 120 | 120 | 0 | 0 | 0 | 0
Story | MGPG9B-36 | Done | Major | Pull all of our existing assets from GitHub into the prototype | 120 | 120 | 0 | 0 | 120 | 120 | 0 | 0 | 0 | 0
Story | MGPG9B-37 | Done | Major | Record a series of videos/gifs of the game ready to implement into the presentation | 120 | 120 | 0 | 0 | 120 | 120 | 0 | 0 | 0 | 0
Story | MGPG9B-38 | Done | Major | Tweak elements of our game to add further refinement | 120 | 120 | 0 | 0 | 120 | 120 | 0 | 0 | 0 | 0
Story | MGPG9B-39 | Done | Major | Anthropomorphise the character concepts | 180 | 180 | 0 | 0 | 300 | 300 | -120 | -120 | -66 | -66
Story | MGPG9B-43 | Done | Major | Design UI mock-ups and Designs | 120 | 120 | 0 | 0 | 120 | 120 | 0 | 0 | 0 | 0
Story | MGPG9B-44 | Done | Major | Draw the penguin character concept into finalized art | 60 | 60 | 0 | 0 | 60 | 60 | 0 | 0 | 0 | 0
Story | MGPG9B-45 | Done | Major | Draw an animation sprite sheet for one or both character art | 180 | 180 | 0 | 0 | 180 | 180 | 0 | 0 | 0 | 0
Story | MGPG9B-47 | Done | Major | Play test the game in order to find and fix any bugs | 60 | 60 | 0 | 0 | 60 | 60 | 0 | 0 | 0 | 0
Story | MGPG9B-50 | Done | Major | Implement the block mechanic | 120 | 120 | 0 | 0 | 120 | 120 | 0 | 0 | 0 | 0
Story | MGPG9B-53 | Done | Major | Using the placeholder art; test and implement the block mechanic | 90 | 90 | 0 | 0 | 90 | 90 | 0 | 0 | 0 | 0
Story | MGPG9B-55 | Done | Major | Code the ball to prevent the player who scored from starting with the ball when it respawns | 90 | 90 | 0 | 0 | 90 | 90 | 0 | 0 | 0 | 0
Story | MGPG9B-56 | Done | Major | Finalise the UI art created in the previous week (created by Mark) | 180 | 180 | 0 | 0 | 180 | 180 | 0 | 0 | 0 | 0
Story | MGPG9B-57 | Done | Major | Finalize the Reindeer and Wolf character art | 60 | 60 | 0 | 0 | 120 | 120 | -60 | -60 | -100 | -100
Story | MGPG9B-58 | Done | Major | Finalise the arena overlay art created in the previous week (created by Mark) | 60 | 60 | 0 | 0 | 60 | 60 | 0 | 0 | 0 | 0
Story | MGPG9B-59 | Done | Major | Merge the two Unity builds together using Charlie's build as the base | 120 | 120 | 0 | 0 | 120 | 120 | 0 | 0 | 0 | 0
Story | MGPG9B-61 | Done | Major | Design and draw the background art to go behind the UI | 120 | 120 | 0 | 0 | 130 | 130 | -10 | -10 | -8 | -8
Story | MGPG9B-62 | Done | Major | Draw placeholder art to be used for the block mechanic during testing | 60 | 60 | 0 | 0 | 60 | 60 | 0 | 0 | 0 | 0
Story | MGPG9B-63 | Done | Major | Draw front facing placeholder art for the reindeer, wolf, penguin and polar bear characters | 180 | 180 | 0 | 0 | 180 | 180 | 0 | 0 | 0 | 0
Story | MGPG9B-64 | Done | Major | Create a questionnaire for when we playtest the game | 120 | 120 | 0 | 0 | 120 | 120 | 0 | 0 | 0 | 0
Story | MGPG9B-65 | Done | Major | Draw the polar bear throwing animation in the form of a sprite sheet | 60 | 60 | 0 | 0 | 60 | 60 | 0 | 0 | 0 | 0
Story | MGPG9B-66 | Done | Major | Draw the Penguin throwing animation in the form of a sprite sheet | 120 | 120 | 0 | 0 | 120 | 120 | 0 | 0 | 0 | 0
Story | MGPG9B-67 | Done | Major | Draw the Reindeer throwing animation in the form of a sprite sheet | 120 | 120 | 0 | 0 | 120 | 120 | 0 | 0 | 0 | 0
Story | MGPG9B-68 | Done | Major | Finalise the wold character art | 60 | 60 | 0 | 0 | 60 | 60 | 0 | 0 | 0 | 0
Story | MGPG9B-69 | Done | Major | Finalise the work on the character selection code | 120 | 120 | 0 | 0 | 120 | 120 | 0 | 0 | 0 | 0
Story | MGPG9B-70 | Done | Major | Playtest the Game and get feedback from peers | 120 | 120 | 0 | 0 | 120 | 120 | 0 | 0 | 0 | 0
Story | MGPG9B-71 | Done | Major | Playtest the Game and get feedback from peers | 120 | 120 | 0 | 0 | 120 | 120 | 0 | 0 | 0 | 0
Story | MGPG9B-72 | Done | Major | Playtest the Game and get feedback from peers | 120 | 120 | 0 | 0 | 120 | 120 | 0 | 0 | 0 | 0
Story | MGPG9B-73 | Done | Major | Design a Goal Event | 180 | 180 | 0 | 0 | 180 | 180 | 0 | 0 | 0 | 0
Story | MGPG9B-74 | Done | Major | Fine Tune the Dash and Block mechanics | 120 | 120 | 0 | 0 | 120 | 120 | 0 | 0 | 0 | 0
Story | MGPG9B-75 | Verify | Major | Re-implement the sounds to the game | 60 | 60 | 0 | 0 | 60 | 60 | 0 | 0 | 0 | 0
Story | MGPG9B-77 | Verify | Major | Design art for the powerbar | 90 | 90 | 0 | 0 | 90 | 90 | 0 | 0 | 0 | 0
Story | MGPG9B-80 | Verify | Major | Program the win condition | 90 | 90 | 0 | 0 | 105 | 105 | -15 | -15 | -16 | -16
Story | MGPG9B-81 | Verify | Major | Program the sudden death condition | 90 | 90 | 0 | 0 | 90 | 90 | 0 | 0 | 0 | 0
Story | MGPG9B-83 | Done | Major | Program a countdown before play resumes | 60 | 60 | 0 | 0 | 60 | 60 | 0 | 0 | 0 | 0
Story | MGPG9B-85 | Done | Major | Implement character animations | 60 | 60 | 0 | 0 | 60 | 60 | 0 | 0 | 0 | 0
Story | MGPG9B-31 | Done | Major | Create the animating wall | 180 | 180 | 10 | 10 | 170 | 170 | 0 | 0 | 0 | 0
Story | MGPG9B-51 | Done | Major | Create art to be used for the instructions screen | 90 | 90 | 15 | 15 | 75 | 75 | 0 | 0 | 0 | 0
Story | MGPG9B-60 | Done | Major | Resize the prototype so there is blank space for UI | 120 | 120 | 15 | 15 | 105 | 105 | 0 | 0 | 0 | 0
Story | MGPG9B-42 | Done | Major | Implement the sounds and UI elements from your previous tasks | 180 | 180 | 20 | 20 | 160 | 160 | 0 | 0 | 0 | 0
Story | MGPG9B-12 | Done | Major | Conceptualise the mechanics and add/subtract in line with your iterations | 120 | 120 | 30 | 30 | 90 | 90 | 0 | 0 | 0 | 0
Story | MGPG9B-17 | Done | Major | Research sounds that might pair well with our game | 180 | 180 | 30 | 30 | 150 | 150 | 0 | 0 | 0 | 0
Story | MGPG9B-18 | Done | Major | Research similar user interfaces and create a moodboard with your results | 180 | 180 | 30 | 30 | 150 | 150 | 0 | 0 | 0 | 0
Story | MGPG9B-49 | To Do | Major | Think up 15 possible names for our game ready for us to go through the following week | 60 | 60 | 30 | 30 | 30 | 30 | 0 | 0 | 0 | 0
Story | MGPG9B-76 | To Do | Major | Work on the presentation ready for next week | 60 | 60 | 30 | 30 | 30 | 30 | 0 | 0 | 0 | 0
Story | MGPG9B-1 | Done | Major | Program the Player movement for our game | 60 | 60 | 60 | 60 |  |  |  |  | 0 | 0
Story | MGPG9B-11 | Done | Major | Design a new art style with accompanying moodboard | 60 | 60 | 60 | 60 |  |  |  |  | 0 | 0
Story | MGPG9B-13 | Done | Major | Iterate on the neon art style in order to come up with a way to implement it whilst being unique | 180 | 180 | 60 | 60 | 120 | 120 | 0 | 0 | 0 | 0
Story | MGPG9B-78 | To Do | Major | Create particle effect for the goal animation | 60 | 60 | 60 | 60 |  |  |  |  | 0 | 0
Story | MGPG9B-79 | To Do | Major | Program the particle effect for the goal animation | 60 | 60 | 60 | 60 |  |  |  |  | 0 | 0
Story | MGPG9B-82 | To Do | Major | Program the powerbar | 120 | 120 | 60 | 60 | 60 | 60 | 0 | 0 | 0 | 0
Story | MGPG9B-86 | To Do | Major | Design the main menu art | 90 | 90 | 90 | 90 |  |  |  |  | 0 | 0
Story | MGPG9B-84 | To Do | Major | Conduct playtesting showcasing the new mechanics | 120 | 120 | 120 | 120 |  |  |  |  | 0 | 0
Story | MGPG9B-20 | Done | Major | Research the art style we have agreed upon and try to learn/replicate it | 180 | 180 | 180 | 180 |  |  |  |  | 0 | 0
Story | MGPG9B-32 | Done | Major | Implement the sounds and UI you created last week | 180 | 180 | 180 | 180 |  |  |  |  | 0 | 0
Story | MGPG9B-46 | To Do | Major | Work on the animating wall | 180 | 180 | 180 | 180 |  |  |  |  | 0 | 0
|  |  |  | Total | 9390 | 9390 | 1320 | 1320 | 8515 | 8515 | -445 | -445 | -4 | -4
Generated at 3/29/17 9:23 AM by Thomas Turner using JIRA 7.2.5#72007-sha1:61b18485286d3e8cee963a8ec9183c3674a7b97d.